## Corrective Action Plan Template
Corrective Action: Example Entry
Field | Sample Content
Finding ID | Unique identifier for the audit finding (e.g., NC-2025-001).
Audit Source | Source of the finding (e.g., SOC 2 Type II, ISO 27001 Stage 1, Internal Risk Assessment).
Category | Risk area or control domain (e.g., Access Control, Vendor Management, Change Management).
Finding / Non-Conformity Description | Detailed description of what was found, including the evidence cited by the auditor. Copy this directly from the Audit Findings Report.
Severity Level | High / Medium / Low — based on impact, likelihood, and regulatory urgency.
Root Cause Analysis | Brief analysis of why this issue occurred. Was it a people, process, or system failure? Was it a one-off or systemic issue?
Corrective Action | Specific steps that will be taken to correct the issue and prevent recurrence. Should go beyond temporary fixes.
Preventive Action (Optional) | Broader improvements (e.g., training, automation, policy changes) that address underlying gaps.
Owner | Person or team responsible for implementing the corrective action.
Target Completion Date | Date by which the corrective action must be completed. Include reasonable timelines with compliance urgency in mind.
Status | Not Started / In Progress / Completed / Verified / Deferred. Consider using color-coding for quick visual reference.
Evidence of Completion | Link or reference to documentation, screenshots, policies, or control evidence that proves the issue has been remediated.
Date Closed | When the issue was officially closed out and verified by an internal or external stakeholder.
Follow-up / Verification Method | How you’ll verify remediation (e.g., re-testing, internal audit, automated scan). Include the reviewer name if available.

## Example Entry
Corrective Action: Example Entry
Field | Sample Content
Finding ID | NC-2025-003
Audit Source | SOC 2 Type II
Category | Access Control
Finding / Non-Conformity Description | Multi-factor authentication (MFA) was not enforced across all critical systems. Evidence showed at least 3 administrative logins without MFA.
Severity Level | High
Root Cause Analysis | MFA was not properly enforced for legacy systems due to oversight in vendor configuration.
Corrective Action | Update MFA policy to include legacy systems. Reconfigure vendor accounts to enforce MFA across all admin-level access points.
Preventive Action (Optional) | Monthly access reviews added. All new systems must be reviewed against access control baseline during onboarding.
Owner | IT Security Lead
Target Completion Date | 2025-08-15
Status | In Progress
Evidence of Completion | Screenshot of admin portal settings. Updated policy document. Access logs showing MFA challenge.
Date Closed | –
Follow-up / Verification Method | Internal audit follow-up + tool-generated MFA status report.